## Escala de tiempo
Tareas | [5 empty] | Hitos
Inicio | Fin | Duración | Etiqueta | Vert. Posición | Vert. Línea | Fecha | Etiqueta | Posición
2023-11-16 | 2023-11-29 | 14 | Perfil de Proyecto nov 16 - nov 29 | -17 | 0 | 2023-11-16 | Inicio, nov 16 | 35
2023-11-29 | 2023-12-14 | 15 | Corrección de Perfil nov 29 - dic 14 | -27 | 0 | 2024-01-24 | Sprint 1 | 30
2023-11-30 | 2023-12-14 | 16 | Revisión de Perfil de Proyecto nov 30 - dic 14 | -35 | 0 | 2024-02-22 | Sprint 2 | 20
2023-11-30 | 2023-12-05 | 5 | Matriz de Requisito | -43 | 0 | 2024-02-24 | Sprint 3 | 15
2023-12-02 | 2023-12-02 | 1 | Reunión 1 con tutor empresarial | -51 | 0 | 2024-02-29 | Entregar, feb 29 | 10
2023-12-08 | 2023-12-08 | 1 | Reunion 2 con tutor empresarial | -55 | 0 |  | Insertar nuevas filas encima de ésta
2023-12-05 | 2023-12-13 | 8 | Corrección de Matriz | -62 | 0
2023-12-05 | 2023-12-14 | 9 | Revisión de Elicitación de Requisitos | -70 | 0
2023-11-07 | 2023-12-15 | 8 | Análisis y Diseño de proyecto | -76 | 0
2023-12-18 | 2024-01-14 | 28 | Desarrollo Requisito 1 - 2 | -82 | 0
2024-01-14 | 2024-01-23 | 9 | Defensa y Revisión Sprint 1 | -90 | 0
2024-01-23 | 2024-01-25 | 2 | Presentación de corrección de errores Sp1 | -100 | 0
2024-02-01 | 2024-02-18 | 17 | Desarrollo Requisito 3 - 4 | -17 | 0
2024-02-20 | 2024-02-22 | 2 | Defensa y Revisión Sprint 2 | -25 | 0
2024-02-20 | 2024-02-22 | 2 | Presentación de corrección de errores Sp2 | -36 | 0
2024-02-22 | 2024-02-28 | 6 | Desarrollo Requisito 4 - 5 - 6 | -70 | 0
2024-02-29 | 2024-02-29 | 1 | Defensa y Revisión Sprint 3 | -80 | 0
2024-02-29 | 2024-02-29 | 1 | Presentación FINAL | -100 | 0
Insertar nuevas filas encima de ésta
Formulas:
Fin = [Inicio]+[Duración]-1

## Information (hidden)
| Visit: | https://www.templatek.com
Important information
We have many free templates and you can download them whenever you want. Some of the templates are premium and require a payment for each or you can also pay an annual subscription to freely download any type of file.
We have templates of the following types:
1. Professional Presentation Templates for PowerPoint and Google Slides
2. Professional document templates for MS Word, editable files.
3. Professional document templates for MS Excel, editable files..
DISCLAIMER:
This template is provided by templatek.com or one of its providers. The use of this template does not imply any type of responsibility for templatek.con or its suppliers.
If you have any complaint or suspect that the content of this template violates the Copyright, please contact us from here.
Help
If you want to know more about how to use this template, or adapt it, extend it or correct any errors, follow this link:
Other templates
You can also download many editable document templates like Word and presentation templates for PowerPoint and Google Slides:
See help →
See other templates →
Contact here →
See templates →